## Slide 1
CONSTRUCTION PROJECT
DELAY RISK PREDICTION SYSTEM
Using SQL & Power BI for Data-Driven Risk Assessment
Syed Rehan Syed Hamedsaleem
Imarticus Learning

## Slide 2
ACKNOWLEDGEMENT
I extend my sincere gratitude to Utkarsh Tiwari for their invaluable guidance and support throughout this capstone project.
I am thankful to Imarticus Learning for providing the resources and environment necessary for this research.
I also appreciate my family and peers for their continuous encouragement.

## Slide 3
OBJECTIVE & MOTIVATION
OBJECTIVE
Develop a predictive risk assessment system to identify construction projects at high risk of delays using SQL and Power BI.
MOTIVATION
• Construction delays cost billions annually
• Lack of early warning systems
• Need for proactive risk management
• Replace gut-feel with data-driven decisions
TECHNICAL CHALLENGE
How to combine multiple risk factors (delays, blocked tasks, issues, weather) into a single meaningful risk score that actually differentiates between projects?

## Slide 4
PROJECT WORKFLOW
1
Data Ingestion
6 CSV files
28 projects, 174K records
2
SQL Processing
MySQL database
Helper tables & aggregation
3
Data Model
Star schema
9 relationships
4
Power BI
43 DAX measures
9 dashboard pages

## Slide 5
DATA INGESTION
File
Records
Description
projects.csv
28
Project master data
tasks.csv
5,746
Individual tasks with critical path
task_progress_updates.csv
137,899
Daily/weekly progress tracking
issues_ncr_rfi.csv
1,609
Issues and non-conformance reports
task_dependencies.csv
8,619
Task dependency relationships
weather_log.csv
20,824
Daily weather and work stoppage
Tool: MySQL Workbench Table Data Import Wizard | Total: 174,525 records

## Slide 6
SQL DATA PREPROCESSING
APPROACH: Multi-stage transformation using helper tables
Stage 1
Dimension Tables
• DimProjects
• DimTasks
• DimDelayReasons
Stage 2
Helper Tables
• 7 temp tables
• ROW_NUMBER()
• Aggregations
Stage 3
Fact Tables
• FactProjectMetrics
• FactTaskProgress
• FactIssues
• FactWeatherImpact
Stage 4
Views
• vw_ProjectRiskSummary
• vw_ContractorPerformance
• vw_CriticalPathRisk

## Slide 7
RISK SCORE METHODOLOGY
CHALLENGE
Initial formula: All projects scored 15.7 (no differentiation)
SOLUTION
Variance analysis: Weight only metrics that actually vary between projects
FINAL FORMULA (Variance-Based Weighting)
Delay Days
53.8% variance
40% weight
Blocked Tasks %
21.6% variance
30% weight
Work Stop Days
17.2% variance
20% weight
Open Issues
18.1% variance
10% weight

## Slide 8
POWER BI DASHBOARD - 9 PAGES
1
Executive Overview
High-level summary for stakeholders
2
Delay Analysis
Root cause analysis of project delays
3
Risk Scorecard
Detailed risk breakdown per project
4
Task Performance
Task completion & critical path status
5
Issue Tracking
NCR, RFI & Safety issue monitoring
6
Weather Impact
Weather-related delay analysis
7
Contractor Performance
Contractor comparison metrics
8
Location Analysis
Geographic risk patterns
9
Predictive Dashboard
Early warning indicators

## Slide 9
PAGE 1: EXECUTIVE OVERVIEW
KEY INSIGHTS
Risk Distribution: 18-21 Low Risk, 5-8 Medium Risk, 2-3 High Risk projects
Projects showing delays require immediate management attention
Dashboard provides real-time visibility into project health

## Slide 10
PAGE 2: DELAY ANALYSIS
KEY INSIGHTS
Material delays account for ~1000 occurrences per project (primary cause)
Strong correlation between risk score and delay days
Scatter plot identifies high-value projects with high delays

## Slide 11
PAGE 3: RISK SCORECARD
KEY INSIGHTS
Projects exceeding 60 risk score require escalation
Table shows which factors contribute most to each project risk
Clear visibility into risk components enables targeted action

## Slide 12
KEY FINDINGS
✓
Risk Score Differentiation Success
Variance-based weighting achieved proper score spread (6.2 to 17.0)
📊
Delay Days Primary Indicator
53.8% variance makes it the best predictor (40% weight in formula)
⚠️
Blocked Tasks Critical
Projects with >14.4% blocked tasks consistently show high risk
📦
Material Delays Dominate
Supply chain issues are primary bottleneck (avg 1000 per project)
👷
Contractor Performance Varies
Top contractors show 30% lower risk scores than bottom performers
📍
Geographic Risk Patterns
Certain locations show consistently higher delays

## Slide 13
FUTURE WORK
Technical Enhancements
• Machine Learning Integration (Random Forest, XGBoost)
• Real-time dashboard with auto-refresh
• Predictive analytics (30/60/90 day forecasts)
• Mobile dashboard for field managers
• Automated email/SMS alerts
Data & Analytics
• Additional data sources (weather API, supplier tracking)
• Granular task tracking with hourly updates
• Root cause analysis with statistical causality
• Scenario planning & what-if analysis
• Industry-wide benchmark database

## Slide 14
THANK YOU
Questions & Discussion
Syed Rehan Syed Hamedsaleem
syedrhn0@gmail.com